## Actions
Homeowners Forum Action Tracker Last updated: 24/03/22
REF # | Status | Meeting raised (date) | Issue | For | Deadline | Outcome / response
1 | Complete | 2021-12-13 | Update and circulate Terms of Reference for further Forum comment. | Amanda Walker & Forum Members | Circulate Dec 21. Comment before next meet. | Sent Dec 2021
2 | Complete | 2021-12-13 | Follow-up with Forum members for any individual access requirement discussions. | Amanda Walker | Dec 2021 | Email sent to all members Dec 2021
3 | Complete | 2021-12-13 | H&S issues raised picked-up directly with 2x Forum members | Rebecca Outram | 2021-12-13 | Completed 13 Dec 2021
4 | Complete | 2021-12-13 | Proposal for prioritisation and improvement plan to be shared and discussed at upcoming meeting(s) | Rebecca Outram (+ Ebrahim Piperdy) | 2022-02-17 | Service improvement plan to be shared with Forum at meeting in March 22
5 | Complete | 2021-12-13 | Put forward reccomendation for standling leaseholder item in Home News to the Editorial Panel. | Amanda Walker | Dec 2021 | Reccomendation made Dec 2021 - forum to help inform regular reccomendations for Home News.
6 | Complete | 2021-12-13 | Put forward reccomendation for Forum announcement in Home News to the Editorial Panel OR do dedicated Homeowner e-news update. | Amanda Walker (+ Ebrahim Piperdy) | HN reccomendation Dec 21 | Reccomendation made Dec 2021 - agreed for Spring 2022 (to be developed collaboratively)
7 | Complete | 2021-12-13 | Share site visit dates with Forum members with a view to providing opportunity for Forum members to join on their estate. | Ebrahim Piperdy | Jan 2021 | Apologies for the delay this will be sent out in advance of the March meeting with dates for March, April & May 2022
8 | Complete | 2021-12-13 | Send 19/20 & 20/21 invoices to JM. | Ebrahim Piperdy | Dec 2021 | Completed 13 Dec 21
9 | Complete | 2021-12-13 | Code of Conduct to be circulated for Forum members to sign. | Amanda Walker & Forum Members | Circulate Dec 21. Sign before next meet. | Sent Dec 2021
10 | Complete | 2021-12-13 | Circulate information on the roles of Chair / Vice Chair. Foum members to nominate themselves before the next meeting. | Amanda Walker & Forum Members | Circulate Dec 21. Nominations before next meet. | Sent Dec 2021
11 | Complete | 2021-12-13 | Circulate and agree next meeting date. | Amanda Walker | Circulate Dec 21 | Completed Dec 2021
12 | Complete | 2022-03-03 | Provide service charge estimates and actuals template options ahead of the next meeting (via AW) | Ebrahim Piperdy | 2022-04-21 | Issued
13 | Complete | 2022-03-03 | Update Service Improvement Plan to reflect comments and input (AW will recirculate) | Ebrahim Piperdy | 2022-04-21 | Issued
14 | Active | 2022-03-03 | EP to liaise with AM to map-out delays and issues in mortgaging process to inform improvements. | Ebrahim Piperdy | 2022-03-01 | EP to update
15 | Active | 2022-03-03 | Develop reccomendations tracker | Amanda Walker / Valerie Oldfield | 2022-04-21 | In progress
16 | Active | 2022-03-03 | Draft Homeowner Forum key scrutiny themes for circulation and comment. | Amanda Walker / Valerie Oldfield | 2022-04-21 | Drafted - to circulate
17 | Complete | 2022-03-03 | Set-up next meeting and agenda options for review with Chair (incl. Vice Chair appointment) | Amanda Walker & Chair | 2022-03-01 | Completed March 2022
18 | Complete | 2022-03-03 | Meet with Chair to discuss and refine role | Amanda Walker | 2022-03-01 | Completed March 2022
19 | Active | 2022-03-03 | Terms of Refernce & Code of Conduct to be circulated and signed by all members | Amanda Walker & Forum Members | 2022-03-01 | Issued 4th / 7th March 2022. All residents to sign
20 | Active | 2022-03-03 | Circulate login details to online Forum documents, once set-up. | Amanda Walker / Valerie Oldfield | 2022-05-01 | Document page currently being set-up
21 | Complete | 2022-03-03 | Draft Home News Arcticle circulated for comments and Forum contributions. | Amanda Walker & Forum Members | 2022-03-11 | Issued 4th March
22 | Active | 2022-03-03 | Liaise with Michael Wailes regarding involvement in the recruitment prcess for Property Manager. | Rebecca Outram / Ebrahim Piperdy | 2022-03-01 | EP to update
23
24
25
26
27
28
29
30