## Priority
Service Improvement Plan 2021
Item | Description | Outcome | Status | Progress Notes | Completion | Anticipated
1 | Shared Ownership & Leasehold Estimates 21/22 | Complete Estimates run for 21/22, within timeline, to be uploaded to our CX system by end of March 21. | Ended | Successfully completed, with expected errors contained and rectified. | 2021-03-15 | N/A
1A |  | Develop more efficient ways to calculate and display estimated charges | Active | Estimates are calcualted in September once Actuals Have been produced. Process is under development currently |  | 2021-10-01
1B |  | Develop Policy and Procedure | Active | Development of processes and policy, once new way has been tried and tested. |  | 2021-11-01
1C |  | Develop clearer Statements for residents | Active | Peabody and Octavia have already developed new statements which is clear and concise. A copy of the statements have been obtained and will be used, once the initial draft of data is ready
2 | Social Rent Increase 21/22 | Rent Increase for Social rent, incl Fair Rent, Supported Housing, CO-OP and fixed Service Charges | Ended | Increase was largely competed 6 weeks earlier than expected. Supported Housing was to assilimilated in the Rent process, but the mechainsms was not compatible, so SH team undertook some of the work. Further work is required to ensure next years calculations are efficient and seemless. | 2021-05-07 | N/A
2A |  | Assimlate Supported Housing process in the Nominal Rent increase Run, which will provide more accuracy and efficency | Active | Supported housing SC and Rent letter format incompatible for current methodoly
3 | Service Charge Actuals 20/21 | Obtain invoice level information for expenditure for 20/21 and put togther Service Charge Actuals | Ended | Finance have provided data level expenditure spreadsheets. Requested further clarity from Finance and invoices backing up expenditure |  | 2021-08-01
3A |  | External Audit of Actuals | Ended | Booked in KPMG for early August to Sample Audit Actuals |  | 2021-08-01
3B |  | Improving Accuracy of Charges | Ended | Ensuring invoices and Expenditure is coded correctly, with the addition of new codes to apply, enabling further accuray when cleansing. Requested from Finance to remove accrual data and credits where suppliers are not providing them |  | 2021-08-01
3C |  | Develop Policy and Procedure | Active | Process to be drived once new methodology has been tested |  | 2022-03-01
4 | Implementation of CX Service Charge Module | Using Actuals data to test module for implementation | Active | Accumulating data and current finance process to ascertain upload point with cleansed data. Requested information from Finance and project group established. Paul Davies Project managing process, with Paul Browning and team as resource, with rents team as leads. |  | 2022-06-01
4A |  | Estimates data derived from Actuals to be used to setup in CX | Not Started |  |  | TBC
4B |  | Re- Introduce regular statements for residents | Active | Acsertaining functionality, with wish list developed. Meetings with Civica set for July and August. Interim Solution to manually commence quartley statement with kickstarter person starting in team July. |  | 2022-03-01
5 | Fair Rent Process | Align fair rents with social rent timeline | Ended | New registrations were completed with the exception of 120 unist, where the delay has been from the valuation officer. Rents were increased within the 2 year valuation period requirement, well under the threshold of the VO valuation | 2021-03-01 | N/A
5A |  | Develop Process & Policy | Not Started | Ensure policy and process is robust to future proof envsaged increases. |  | 2022-09-01
6 | Section 22 Requests | Create process to ensure timelines are met, with accuracy | Ended | Meeting with finance completed. Agreed they would provide invoices for schemes when collating exepnditure for actuals. Piloting 2 schemes. |  | 2021-08-01
7A | Section 20 Recharge and Planning | Liaise wth Propoerty Sevices to create a recharge policy for mjow works under section 20 | Ended | Initial project meeting competed and information obtained for context. Initial draft complete, with adjustments outstanding the Hexagon credit licence information |  | 2021-08-01
7B |  | Working with homeowners to plan ahead in advance for large scale works being carried out and ensuring there exists Long Term Agreements | Active | In conjunction with 7a, to work with Property Services to meet with all relevant homeowners prior to any section 20 being issued, to work with homeowners in identifying reasonable contractors to carry out works and evidencing quality and reliability of works e.g. avoiding continuous repairs to gate when not reasonable to recharge if repetitively brakes down. Also Long Term Agreements in place with full discussions, thoughts and opinions considered of homeowners. |  | 2022-09-01
8 | Key sites and relationships – Parkspring Court, Patrick Court, Solarium Court, Lyles Court | Ensure relationships are maintiained to a satisfactory level | Active | Communication with key residents is maintained wit repsonding to queries specifically to Service Charge and adjustemts made where necessary. Historical issues gradually being resolved e.g. Parkspring Court with correct apportionments, non works carried out at Lyles Court tackled. Inspections to be booked in and likely to be during actuals process for 21-22 but to review feedback from 2 x inspections carried out to date. |  | Ongoing
9 | Management fee review | Ensure collection of MF reflects expenditure and is value for customers. | Ended | Initial analysis completed. Proposal of the options, 1. Curent Model, 2. Based on expenditure, 3. Percentage. Completed and agreed that no increase at this present time with further reviews in the future. Fixed fees for homeowners continue to remain but do require some analysis for section 20 consultation. |  | 2022-03-01
10 | Performance Management | Develop a suite of key performance information | Active | To be discussed with the forum with ideas proposed e.g. new templates out on time, amendments made, customer service response times etc. |  | 2022-04-01
11 | Service Charge Notifications | Work with the Forum to improve the presentation, format and information provided to homeowners for service charge actuals and service charge estimates | Active | 2 x inspections have completed for members of the Forum, remaining inspections to be scheduled in, example as agreed by the Chair provided to the Forum for comments. All recent notices sent to homeowners provided to Forum for input as to what needs to change in order to make information be more transparent, presentable and informative. |  | 2022-08-01
12 | Staircasing and Remortgage Processs | Work with the Forum to ensure there are no delays to these processes and if they are encountered then issues are speedily resolved | Active | Establishing what the blockages were that one member of the forum encountered, to then review the process and ensure this is prevented. Appears at first glance to relate to administration of documents that historically werent able to be retrieved which blocked the relevant process, colleagues within the new team must be able to obtain documents and other information quickly and easily. |  | 2022-09-01
13 | Mixed Tenure Blocks | Discuss ideas with the forum in how to deliver a service for all customers which relate to mixed tenure blocks | Active | To be discussed with the forum e.g. examples of CCTV, Lyles Court example where general inspection/survey report will be provided to all homeowners only so that can work with other colleagues to carry out repairs with the thoughts of all customers. |  | 2022-10-01
14 | Homeownership Team Staffing | Work with relevant forum member(s) with Property Manager role, inclusive of remit of role, recruitment and interview process | Active | To be discussed at Forum. |  | 2022-06-01

## Secondary
Item | Description | Outcome | Status | Progress Notes | Completion | Anticipated
1 | Direct Debit | Separate DD from July run to April Runs | Not Started | Data obtained |  | 2021-11-01
2 | Rents and Servic Charge Annual Schedule | Develop Annual Schedule incl new processes | Ended | Completed | 2021-05-01
3 | White goods incorrect charge | Greehaven properties have been charged WG when they should not have, refund to be organised | Active | 66 Greenhaven has been refunded. Other properties need to be indentified. CX team are to provide data to identify, but are too busy to provide |  | 2021-11-01
4 | Lease Extension Decision | DG to decide whether SO can extend their lease without staircasing | Active | Awaiting Decision |  | 2021-07-01

## Notices Template Options
Actuals | Comment | Estimates | Comment
Pictures and evidencing works carried out at scheme | Enable confidence that can recharge whilst showing there has been quality and transparancy